## SCRUM-164
SCRUM-164 · Queue of equipment requests awaiting review (Technical Support Staff)
AC1: Given equipment requests exist that are not yet resolved, when I open my queue, then each is listed with its event, event date, requested items and quantities. AC2: Given I sort the queue by event date, when the list reloads, then the soonest event appears first. AC3: Given an equipment request has status fulfilled or unable to fulfil, when I open the queue, then it no longer appears as outstanding. AC4: Given an equipment request has status partially fulfilled with at least one unavailable item, when I open the queue, then it remains listed as outstanding and shows how many items are still unavailable. AC5: Given equipment requests exist for events at every location, when any Technical Support Staff member opens the queue, then all of them are listed, because Technical Support Staff are not scoped to particular equipment types or locations. Customer clarification refs: #19, #66, #90 Fixture F (requests raised in the order A, C, B): EVT-A Bugis Seminar Room, 5 Nov 2026, Projector P-100 ×2 + Wireless Mic WM-3 ×4, not yet resolved ¦ EVT-B Marina Bay Ballroom, 28 Oct 2026, Lectern LC-1 ×1 + Lectern LC-1 ×2 (two lines), not yet resolved ¦ EVT-C Jurong East Training Room, 12 Nov 2026, Projector ×1 (reserved) + Mic ×2 (unavailable) + Lectern ×1 (unavailable), partially fulfilled ¦ EVT-D Bugis Seminar Room, 30 Oct 2026, Projector ×3, fulfilled ¦ EVT-E Marina Bay Ballroom, 2 Nov 2026, Mic ×1, unable to fulfil. Accounts: tech-support@example.com and tech-support-2@example.com (Technical Support Staff), coordinator@example.com (Event Coordinator).
Test Case ID | Test Type | AC | Test Scenario | Pre-conditions | Test Steps | Test Data | Expected Result | Created By* | Date of Creation* | Actual Result | Pass/Fail/Not Executed/Blocked | Remarks | Executed By* | Date of Execution*
TC-164-01 | Happy Path | 1 | Each outstanding request shows its event, event date, requested items and quantities | Fixture F; signed in as tech-support@example.com (Technical Support Staff) | 1. Open /equipment-queue 2. Find EVT-A's row | EVT-A: Projector P-100 ×2, Wireless Mic WM-3 ×4 | EVT-A is listed with its event name, 5 Nov 2026, Projector P-100 ×2 and Wireless Mic WM-3 ×4 (AC1) | arwen | 18/10/26 | Automated: EVT-A (under review) is listed with its event name and reference, 2026-11-05, Projector P-100 ×2 and Wireless Mic WM-3 ×4, read back from the stored rows. | Pass | Automated: tests/integration/equipment-queue.test.ts (TC-164-01); tests/unit/equipment-queue.test.ts (under review is outstanding). | arwen | 18/10/26
TC-164-02 | Boundary | 1 | The same item requested on two lines is shown as two lines, not merged | Fixture F; signed in as tech-support@example.com | 1. Open the queue 2. Find EVT-B's row | EVT-B: Lectern LC-1 ×1 and Lectern LC-1 ×2 as separate lines | Both lines shown with their own quantities (×1 and ×2), not one Lectern ×3 line (AC1) | arwen | 18/10/26 | Automated: EVT-B's two Lectern LC-1 lines come back as two lines, ×1 and ×2, not one ×3 line. | Pass | Boundary. SCRUM-160 AC3 keeps a repeated item as separate lines; the queue must show what was actually requested. ¦ Automated: tests/integration/equipment-queue.test.ts (TC-164-02). | arwen | 18/10/26
TC-164-03 | Negative | 1 | An account without the Technical Support role cannot open the queue | Fixture F; signed in as coordinator@example.com (Event Coordinator only) | 1. Open /equipment-queue 2. Call the queue API directly | — | Page is refused (redirect or access denied); API returns 403 with no equipment request data (AC1: "my queue") | arwen | 18/10/26 | Automated (API half): GET /api/equipment-queue returns 403 to coordinator, operations_manager, venue_staff, event_organiser and attendee, and the queue is never read; 401 with no session. Page half (opening /equipment-queue as coordinator@example.com) not yet run. | Not Executed | Security check. Regression – SCRUM-69 permission matrix. ¦ Automated: tests/unit/equipment-queue-route.test.ts (TC-164-03). Page half to run manually. | arwen | 18/10/26
TC-164-04 | Happy Path | 2 | Sorting by event date puts the soonest event first | Fixture F; signed in as tech-support@example.com | 1. Open the queue 2. Sort by event date | 28 Oct / 5 Nov / 12 Nov 2026 | Order after reload: EVT-B (28 Oct), EVT-A (5 Nov), EVT-C (12 Nov) (AC2) | arwen | 18/10/26 | Automated: sorted by event date the queue reads EVT-B (2026-10-28), EVT-A (2026-11-05), EVT-C (2026-11-12) from Postgres; ?sort=event-date reaches the service. | Pass | Automated: tests/integration/equipment-queue.test.ts, tests/unit/equipment-queue.test.ts, tests/unit/equipment-queue-route.test.ts (TC-164-04). | arwen | 18/10/26
TC-164-05 | Boundary | 2 | Sort uses the date itself, not the displayed text, across a month and year boundary | Fixture F plus EVT-G (Bugis Seminar Room, 3 Jan 2027, Projector ×1) and EVT-H (Marina Bay Ballroom, 28 Dec 2026, Mic ×1), both not yet resolved | 1. Open the queue 2. Sort by event date | 28/12/26 vs 03/01/27 | Order: EVT-B, EVT-A, EVT-C, EVT-H (28 Dec 2026), EVT-G (3 Jan 2027). EVT-G is last, not first as "03/01" would sort as text (AC2) | arwen | 18/10/26 | Automated: by event date the order is EVT-B, EVT-A, EVT-C, EVT-H (2026-12-28), EVT-G (2027-01-03); 3 Jan 2027 sorts last. | Pass | Boundary. Catches sorting on the dd/mm text or ignoring the year. ¦ Automated: tests/unit/equipment-queue.test.ts (TC-164-05), on fixture entries rather than stored rows. | arwen | 18/10/26
TC-164-06 | Negative | 2 | Queue is not ordered by when the request was raised | Fixture F (EVT-A's request raised before EVT-B's, but EVT-B's event is sooner); signed in as tech-support@example.com | 1. Open the queue 2. Sort by event date 3. Refresh the page | EVT-A raised first (5 Nov event); EVT-B raised later (28 Oct event) | EVT-B appears above EVT-A after the sort and still after the refresh (AC2) | arwen | 18/10/26 | Automated: by event date EVT-B is above EVT-A although EVT-A was raised first; the default order is the order raised (A, C, B). Refresh step not yet run. | Not Executed | Automated: tests/integration/equipment-queue.test.ts, tests/unit/equipment-queue.test.ts (TC-164-06). Refresh step to run manually. | arwen | 18/10/26
TC-164-07 | Happy Path | 3 | A fulfilled request no longer appears as outstanding | Fixture F; signed in as tech-support@example.com | 1. Open the queue | EVT-D: fulfilled | EVT-D is not listed as outstanding; EVT-A, EVT-B and EVT-C are (3 outstanding) (AC3) | arwen | 18/10/26 | Automated: EVT-D (fulfilled) is not listed; EVT-A, EVT-B and EVT-C are. | Pass | Status set by SQL until the story that records fulfilment exists (no status column yet). ¦ Automated: tests/integration/equipment-queue.test.ts, tests/unit/equipment-queue.test.ts (TC-164-07). Status set by hand (D-19). | arwen | 18/10/26
TC-164-08 | Negative | 3 | An unable-to-fulfil request is not left in the queue even though nothing was supplied | Fixture F; signed in as tech-support@example.com | 1. Open the queue 2. Look for EVT-E | EVT-E: unable to fulfil | EVT-E is not listed as outstanding (AC3) | arwen | 18/10/26 | Automated: EVT-E (unable to fulfil) is not listed. | Pass | Unable to fulfil counts as resolved, not pending. Status set by SQL until the story that records fulfilment exists (no status column yet). ¦ Automated: tests/integration/equipment-queue.test.ts, tests/unit/equipment-queue.test.ts (TC-164-08). Status set by hand (D-19). | arwen | 18/10/26
TC-164-09 | Boundary | 3 | A request drops off as soon as its last unavailable item is resolved | EVT-C partially fulfilled with only Lectern ×1 still unavailable; signed in as tech-support@example.com | 1. Open the queue: EVT-C listed, 1 still unavailable 2. Reserve the Lectern so EVT-C becomes fulfilled 3. Reload the queue | Unavailable 1 → 0 | Step 1: EVT-C listed. Step 3: EVT-C no longer listed as outstanding (AC3) | arwen | 18/10/26 | Automated: a partially fulfilled request with Lectern ×1 unavailable is listed with 1 unavailable; once the Lectern is no longer unavailable and the status is fulfilled, it is not listed. | Pass | Boundary between AC4 (≥1 unavailable) and AC3 (fulfilled). Reservation is D-18's stand-in until SCRUM-167. Status set by SQL until the story that records fulfilment exists (no status column yet). ¦ Automated: tests/integration/equipment-queue.test.ts (TC-164-09). Line and status changed by hand (D-19), standing in for the reservation. | arwen | 18/10/26
TC-164-10 | Happy Path | 4 | A partially fulfilled request stays listed and shows how many items are still unavailable | Fixture F; signed in as tech-support@example.com | 1. Open the queue 2. Find EVT-C's row | EVT-C: Projector ×1 reserved, Mic ×2 unavailable, Lectern ×1 unavailable | EVT-C is listed as outstanding and shows 2 items still unavailable (Mic and Lectern), not 3 (all items requested) and not 3 units (Mic ×2 + Lectern ×1) (AC4) | arwen | 18/10/26 | Automated: EVT-C (3 lines) is listed as partially fulfilled with 2 items still unavailable, not 3. | Pass | PO (18 Oct): "how many items" is the number of unavailable items, each counted once whatever its quantity. Status set by SQL until the story that records fulfilment exists (no status column yet). ¦ Automated: tests/integration/equipment-queue.test.ts, tests/unit/equipment-queue.test.ts (TC-164-10). Status and unavailable lines set by hand (D-19). | arwen | 18/10/26
TC-164-11 | Boundary | 4 | One unavailable item is enough to keep a request listed | EVT-C partially fulfilled: Projector and Mic reserved, Lectern ×1 unavailable; signed in as tech-support@example.com | 1. Open the queue 2. Find EVT-C's row | Unavailable = 1 | EVT-C is listed as outstanding and shows 1 item still unavailable (AC4) | arwen | 18/10/26 | Automated: with one unavailable line the request is listed as partially fulfilled and the count is 1. | Pass | Boundary. The lowest count AC4 covers; at 0 it is fulfilled (TC-164-09). Status set by SQL until the story that records fulfilment exists (no status column yet). ¦ Automated: tests/unit/equipment-queue.test.ts (TC-164-11); tests/integration/equipment-queue.test.ts (TC-164-09, first read). | arwen | 18/10/26
TC-164-12 | Negative | 4 | The unavailable count is not stale after an item is reserved | Fixture F (EVT-C, 2 unavailable); signed in as tech-support@example.com | 1. Open the queue: EVT-C shows 2 still unavailable 2. Reserve the Mic 3. Reload the queue | Unavailable 2 → 1 | EVT-C is still listed and now shows 1 item still unavailable, not 2 (AC4) | arwen | 18/10/26 | Automated: a partially fulfilled request with Mic and Lectern unavailable shows 2; after the Mic is no longer unavailable it is still listed and shows 1. | Pass | Reservation is D-18's stand-in until SCRUM-167. Status set by SQL until the story that records fulfilment exists (no status column yet). ¦ Automated: tests/integration/equipment-queue.test.ts (TC-164-12). Line changed by hand (D-19), standing in for the reservation. | arwen | 18/10/26
TC-164-13 | Happy Path | 5 | Requests for events at every location are listed | Fixture F (Bugis, Marina Bay and Jurong); signed in as tech-support@example.com | 1. Open the queue | EVT-A Bugis, EVT-B Marina Bay, EVT-C Jurong | EVT-A, EVT-B and EVT-C are all listed (AC5) | arwen | 18/10/26 | Automated: EVT-A (items kept at Bugis Store Room), EVT-B (item kept at Marina Bay Store Room) and EVT-C are all listed; nothing filters by location or equipment type. | Pass | Automated: tests/integration/equipment-queue.test.ts (TC-164-13). The test events have no venue booking; the queue does not read the venue. | arwen | 18/10/26
TC-164-14 | Negative | 5 | The queue is not scoped to the Technical Support member viewing it | Fixture F; a second account tech-support-2@example.com (Technical Support Staff) | 1. As tech-support@example.com, open the queue and note the list 2. Sign in as tech-support-2@example.com and open the queue | Two Technical Support accounts | Both see the same 3 requests with the same items and order; nothing is filtered by viewer, equipment type or location (AC5) | arwen | 18/10/26 |  | Not Executed
TC-164-15 | Boundary | 5 | A request at a newly added location, with equipment stored elsewhere, is listed without any setup | Fixture F plus a new location "Tampines" added to the locations list today, with a new venue Tampines Hall in it; EVT-I (Tampines Hall, 18 Nov 2026) requests Lectern LC-1 ×1 (stored at Marina Bay Store Room) | 1. As tech-support@example.com, open the queue 2. As tech-support-2@example.com, open the queue | New location, first request; equipment from another location's store room | EVT-I is listed for both accounts (AC5) | arwen | 18/10/26 |  | Not Executed | Boundary. A location with no earlier requests, and an item stored at a different location.