## SCRUM-142
SCRUM-142 : Submit a venue booking request for an event
AC1: Given I am the assigned coordinator of an event that is Approved or in Planning, when I submit a booking request naming one venue, a date and the required slots, then the request is created with status Pending. AC2: Given an event has not been approved, when I attempt to create a booking request, then the action is refused and I am told the event must be approved before venue arrangements begin. AC3: Given my event needs the same venue on several dates, when I submit the request, then every requested date and slot is carried on the one request and each date and slot line carries its own decision status of Pending. AC4: Given I am an Event Coordinator who is not assigned to the event, when I invoke a booking request action on it, then it is refused and no request is created. AC5: Given a mandatory field (date, timing or venue requirements) is left empty, when the assigned coordinator of an approved event attempts to create the request, then the request is not created and the missing fields are identified.
Test Case ID | Test Type | AC | Test Scenario | Pre-conditions | Test Steps | Test Data | Expected Result | Created By* | Date of Creation* | Actual Result | Pass/Fail/Not Executed/Blocked | Automated / Manual | Result | Executed By | Date of Execution*
TC-142-01 | Happy Path | 1 | Booking request succeeds when the event is Approved | Event status is Approved; actor is the assigned coordinator | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Approved and assigned to the coordinator; mock the venue as open all day with nothing committed 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '13:00', end: '18:00' }] }) (PM is 13:00-18:00) 3. Check createVenueBookingRequest was called once and the outcome has one line with status pending Integration (submit-venue-booking-request.test.ts), real local database: 1. Create an Approved event assigned to the coordinator 2. Make the same call 3. Read the request and its lines back from Postgres | Venue: Marina Ballroom; Date: 15 Nov 2026; Slot: PM | One venue booking request is created for that venue with one date/slot line, status Pending (AC1) | Arwen | 27/09/26 | One request row (right venue, requested_by = the coordinator) with one line: 2026-11-15, [pm], status pending, read back from Postgres | Pass | Automated | Automated: unit (venue-booking-service.test.ts) + real local database (submit-venue-booking-request.test.ts). | Arwen | 03/10/26
TC-142-01 | Happy Path | 1 | Booking request succeeds when the event is Approved | Event status is Approved; actor is the assigned coordinator | 1. Open the accepted event request 2. Click on Venue Booking Request 3. Select a venue, a date, a slot 4. Submit | Venue: Marina Ballroom; Date: 15 Nov 2026; Slot: PM | One venue booking request is created for that venue with one date/slot line, status Pending (AC1) | Arwen | 27/09/26 | Shows venue booking request is submitted. The Venue Staff queue page itself is SCRUM-147; the row exists and is readable. | Pass | Manual | Manual run. Edit: discussed with PR reviewer and Product Owner that the AC should be changed to remove checking that the event request lands in the Venue Staff queue, since it will be created in a later user story. | Arwen | 11/10/26
TC-142-02 | Happy Path | 1 | Booking request succeeds when the event is already in Planning | Event status is Planning; actor is the assigned coordinator | Unit (venue-booking-policy.test.ts): 1. Call canCreateBookingRequest('planning') and canCreateBookingRequest('approved'); both must return true Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Planning and assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '13:00', end: '18:00' }] }) 3. Check createVenueBookingRequest was called once and every line has status pending | Venue: Bugis Seminar Room; Date: 15 Nov 2026; Slot: AM, PM | Second request created, status Pending (AC1) | Arwen | 27/09/26 | One request row (Bugis Seminar Room) with one line: 2026-10-15, [pm, am], status pending, read back from Postgres. | Pass | Automated | Automated: unit (venue-booking-policy.test.ts, venue-booking-service.test.ts). | Arwen | 03/10/26
TC-142-02 | Happy Path | 1 | Booking request succeeds when the event is already in Planning | Event status is Planning; actor is the assigned coordinator | 1. Move a test event from Approved to Planning using the SCRUM-103 manual-test harness (tests/manual/change-event-status.test.ts) 2. Sign in as the assigned coordinator and open the event's review page; confirm the status badge reads Planning 3. In "Request a venue", select a venue, a date and two slots 4. Click Request venue | Venue: Bugis Seminar Room; Date: 15 Nov 2026; Slot: AM, PM | Second request created, status Pending (AC1) | Arwen | 27/09/26 | The "Request a venue" section was shown for the Planning event. Submitting displayed "Venue booking request submitted — 1 date pending Venue Staff review." The event stayed in Planning. | Pass | Manual | Manual: Venue booking request submitted — 1 date pending Venue Staff review. | Arwen | 03/10/26
TC-142-03 | Negative | 2 | Booking request blocked when the event has not been approved (Draft / Submitted / Clarification requested) | Event status is not Approved; actor is the assigned coordinator | Unit (venue-booking-service.test.ts), data layer mocked: For each status draft, submitted, clarification_requested and rejected: 1. Mock the event with that status, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '13:00', end: '18:00' }] }) 3. Expect a VALIDATION_ERROR whose message says the event must be approved before venue arrangements; check createVenueBookingRequest was not called Integration (submit-venue-booking-request.test.ts), real local database: For each status submitted and rejected (a Draft cannot hold a coordinator in the database, so Draft is unit only): 1. Create an event in that status, assigned to the coordinator 2. Make the same call and expect the same refusal 3. Read the event's requests back from Postgres: none | Event status: draft, submitted, clarification_requested (one run each); valid venue/date/slot | Refused with 'The event must be approved before venue arrangements can begin.'; no request created (AC2) | Arwen | 27/09/26 | Each refused with that message; no request rows written (Submitted checked in Postgres; Draft and Clarification requested in unit tests). | Pass | Automated | Automated: unit (venue-booking-service.test.ts); Submitted and Rejected also run against the real local database. | Arwen | 03/10/26
TC-142-03 | Negative | 2 | Booking request blocked when the event has not been approved (Draft / Submitted / Clarification requested) | Event status is not Approved; actor is the assigned coordinator | 1. Attempt to create a request | Event status: draft, submitted, clarification_requested (one run each); valid venue/date/slot | Refused with 'The event must be approved before venue arrangements can begin.'; no request created (AC2) | Arwen | 27/09/26 | 1. Event is in 'Submitted' status → No venue booking request button. 2. Event is in 'Clarification Requested' status → No venue booking request button. 3. Event in 'Draft' status → won't even be assigned to Event Coordinator. | Pass | Manual | Manual: 1. Event is in 'Submitted' status → No venue booking request button. 2. Event is in 'Clarification Requested' status → No venue booking request button. 3. Event in 'Draft' status → won't even be assigned to Event Coordinator. | Arwen | 03/10/26
TC-142-04 | Negative | 2 | Booking request blocked when the event has been Rejected | Event status is Rejected; actor is the assigned coordinator | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Rejected, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '13:00', end: '18:00' }] }) 3. Expect a VALIDATION_ERROR saying the event must be approved; check createVenueBookingRequest was not called Integration (submit-venue-booking-request.test.ts), real local database: 1. Create a Rejected event assigned to the coordinator 2. Make the same call and expect the same refusal 3. Read the event's requests back from Postgres: none | Event status: rejected; valid venue/date/slot | Refused with the 'must be approved' message; no request created (AC2) | Arwen | 27/09/26 | Refused with that message; no request rows written (checked in Postgres). | Pass | Automated | Automated: unit (venue-booking-service.test.ts); also run against the real local database. | Arwen | 03/10/26
TC-142-04 | Negative | 2 | Booking request blocked when the event has been Rejected | Event status is Rejected; actor is the assigned coordinator | 1. Attempt to create a request | Event status: rejected; valid venue/date/slot | Refused with the 'must be approved' message; no request created (AC2) | Arwen | 27/09/26 | No Venue Booking Request button is shown upon opening the closed event request details. | Pass | Manual | Manual: No Venue Booking Request button is shown upon opening the closed event request details. | Arwen | 03/10/26
TC-142-05 | Happy Path | 3 | One request covers the same venue on two dates | Event status is Approved; actor is the assigned coordinator | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '13:00', end: '18:00' }, { date: '2026-11-16', start: '09:00', end: '11:00' }] }) 3. Check createVenueBookingRequest was called once, there is one request id, and the two lines have different ids and status pending Integration (submit-venue-booking-request.test.ts), real local database: 1. Create an Approved event assigned to the coordinator 2. Make the same call 3. Read back from Postgres: one request with two lines, both pending | Venue: Marina Bay Ballroom; Dates: 15 Nov 2026 (PM) & 16 Nov 2026 (AM) | ONE request carrying both dates and slots; each date/slot line has its own status Pending (AC3) | Arwen | 27/09/26 | One request row with two lines (15 Nov PM, 16 Nov AM), both pending, read back from Postgres. | Pass | Automated | Automated: unit (venue-booking-service.test.ts) + real local database (submit-venue-booking-request.test.ts). | Arwen | 03/10/26
TC-142-05 | Happy Path | 3 | One request covers the same venue on two dates | Event status is Approved; actor is the assigned coordinator | 1. Open the venue booking form 2. Select a venue 3. Add two dates, each with a slot 4. Submit | Venue: Marina Bay Ballroom; Dates: 15 Nov 2026 (PM) & 16 Nov 2026 (AM) | ONE request carrying both dates and slots; each date/slot line has its own status Pending (AC3) | Arwen | 27/09/26 | Recorded both dates and timeslots. | Pass | Manual | Manual run: Recorded both dates and timeslots. | Arwen | 11/10/26
TC-142-06 | Boundary | 1, 3 | One request covers more than one slot on the same date | Event status is Approved; actor is the assigned coordinator | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '09:00', end: '11:00' }, { date: '2026-11-15', start: '14:00', end: '16:00' }] }) (two periods on one date, since slots became times) 3. Check createVenueBookingRequest was called once, and both lines come back pending in their start and end order Integration (submit-venue-booking-request.test.ts), real local database: 1. Create an Approved event assigned to the coordinator 2. Make the same call 3. Read back from Postgres: one request with two lines on 2026-11-15 | Venue: Marina Bay Ballroom; Date: 15 Nov 2026; Slots: AM, PM | One request; the date carries both slots; status Pending (AC1, AC3) | Arwen | 27/09/26 | One request, one line carrying [am, pm], status pending, read back from Postgres. The DB defaults each line to pending. | Pass | Automated | Automated: unit (venue-booking-service.test.ts) + real local database (submit-venue-booking-request.test.ts). | Arwen | 11/10/26
TC-142-06 | Boundary | 1, 3 | One request covers more than one slot on the same date | Event status is Approved; actor is the assigned coordinator | 1. Select a venue and one date 2. Tick two slots 3. Submit | Venue: Marina Bay Ballroom; Date: 15 Nov 2026; Slots: AM, PM | One request; the date carries both slots; status Pending (AC1, AC3) | Arwen | 27/09/26 | Recorded both timeslots. The slots sit together in one line per date. | Pass | Manual | Manual run: recorded both timeslots. The slots sit together in one line per date. | Arwen | 10/10/26
TC-142-07 | Negative | 4 | A coordinator who is not assigned cannot submit | Event is assigned to a different coordinator | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock an Approved event assigned to a different coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '13:00', end: '18:00' }] }) as the first coordinator 3. Expect a FORBIDDEN error; check createVenueBookingRequest was not called 4. Repeat with an event that has no coordinator (FORBIDDEN), with a Draft event assigned to someone else (FORBIDDEN, and the message does not mention approval), and with an event that does not exist (NOT_FOUND) Integration (submit-venue-booking-request.test.ts), real local database: 1. Create an Approved event assigned to coordinator A 2. Call as coordinator B 3. Expect FORBIDDEN and no rows in Postgres | Actor id differs from the event's coordinator; valid venue/date/slot | Refused (Forbidden); no request created (AC4) | Arwen | 27/09/26 | Refused with FORBIDDEN; no request rows written (checked in Postgres). Same result when the event has no coordinator, and the refusal does not reveal the event status. | Pass | Automated | Automated: unit (venue-booking-service.test.ts) + real local database (submit-venue-booking-request.test.ts). | Arwen | 10/10/26
TC-142-07 | Negative | 4 | A coordinator who is not assigned cannot submit | Event is assigned to a different coordinator | 1. Attempt to submit as the other coordinator | Actor id differs from the event's coordinator; valid venue/date/slot | Refused (Forbidden); no request created (AC4) | Arwen | 27/09/26 | Refused with FORBIDDEN. | Pass | Manual | Manual run: Refused with FORBIDDEN. | Arwen | 10/10/26
TC-142-08 | Negative | 4 | An Event Organiser cannot submit a venue booking request | Actor holds the Event Organiser role | Unit (venue-booking-service.test.ts), data layer mocked: 1. Call isActionPermitted(['event_organiser'], 'venue_booking_request'); it must return false 2. Call assertPermission(['event_organiser'], 'venue_booking_request'); it must throw FORBIDDEN 3. As a control, the 'coordinator' role must be permitted (The route runs this check before the service, so the service is never called.) | Role: event_organiser | Refused at the route's permission check; service never reached | Arwen | 27/09/26 | Permission check refuses event_organiser. Supplementary — the role gate is SCRUM-69's matrix, run by the route before the service; attendee, technical_support and operations_manager are also refused. | Pass | Automated | Automated (venue-booking-service.test.ts). | Arwen | 10/10/26
TC-142-08 | Negative | 4 | An Event Organiser cannot submit a venue booking request | Actor holds the Event Organiser role | 1. Attempt the action | Role: event_organiser | Refused at the route's permission check; service never reached | Arwen | 27/09/26 | Refused with FORBIDDEN. | Pass | Manual | Manual run: Refused with FORBIDDEN. | Arwen | 10/10/26
TC-142-09 | Negative | 4 | A Venue Staff member cannot submit a venue booking request | Actor holds the Venue Staff role | Unit (venue-booking-service.test.ts), data layer mocked: 1. Call isActionPermitted(['venue_staff'], 'venue_booking_request'); it must return false 2. Call assertPermission(['venue_staff'], 'venue_booking_request'); it must throw FORBIDDEN 3. As a control, the 'coordinator' role must be permitted (The route runs this check before the service, so the service is never called.) | Role: venue_staff | Refused at the route's permission check; service never reached | Arwen | 27/09/26 | Permission check refuses venue_staff. Supplementary, same reason as TC-142-08. | Pass | Automated | Automated (venue-booking-service.test.ts). Supplementary, same reason as TC-142-08. | Arwen | 11/10/26
TC-142-09 | Negative | 4 | A Venue Staff member cannot submit a venue booking request | Actor holds the Venue Staff role | 1. Attempt the action | Role: venue_staff | Refused at the route's permission check; service never reached | Arwen | 27/09/26 | Refused with FORBIDDEN. | Pass | Manual | Manual run: Refused with FORBIDDEN. | Arwen | 22/10/26
TC-142-10 | Negative | Supp. | A retired venue cannot be requested | Venue is marked retired (is_retired = true); event is Approved; actor is the assigned coordinator | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock an Approved event assigned to the coordinator, and mock getVenue to return the venue with isRetired = true 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '13:00', end: '18:00' }] }) 3. Expect a VALIDATION_ERROR whose message says the venue is retired, flagging venueId; check createVenueBookingRequest was not called Integration (submit-venue-booking-request.test.ts), real local database: 1. Create a venue and set is_retired = true; create an Approved event assigned to the coordinator 2. Call with the retired venue's id 3. Expect the same refusal; read back from Postgres: no request, and the event is still Approved | Venue: Bugis Old Annex (retired, seed.sql); Event: EVT-2026-0093 (Approved); Date: 15 Nov 2026; Slot: PM | Retired venue not offered in the form; a direct request is refused and nothing is created | Arwen | 27/09/26 | API: 400 "This venue is retired, so it cannot be requested."; no request row written and the event stays Approved. Covered by unit and integration tests. | Pass | Automated | Automated: unit and integration tests (fixed on branch scrum-142-bug, commit fdd1491, PR #91). Supplementary, not a Jira AC. Refer to SCRUM-245 for fixes. | Arwen | 22/10/26
TC-142-10 | Negative | Supp. | A retired venue cannot be requested | Venue is marked retired (is_retired = true); event is Approved; actor is the assigned coordinator | 1. Open the event's venue booking form and check the venue dropdown 2. Send the request directly to the API with the retired venue's id | Venue: Bugis Old Annex (retired, seed.sql); Event: EVT-2026-0093 (Approved); Date: 15 Nov 2026; Slot: PM | Retired venue not offered in the form; a direct request is refused and nothing is created | Arwen | 27/09/26 | Form: Bugis Old Annex is not in the dropdown. | Pass | Manual | Manual. Failed on first run, 10/10/26: the API accepted a retired venue, created a Pending request and moved the event to Planning before the fix. | Arwen | 22/10/26
TC-142-11 |  | Supp. | A multi-session event can have a separate request per session | Event has two sessions | 1. Submit a request per session | Two sessions | Two independent requests | Arwen | 27/09/26 | Not executed: withdrawn. An event request has no 'sessions' in the data model (event_request has no session table or column), so there is nothing to run, even with a dummy. | Not Executed | n/a (withdrawn) | Withdrawn 11/10/26. Not an AC on the Jira card. A dummy would mean inventing a sessions concept that isn't on the card, and the test would prove nothing. Several requests for one event are already covered by TC-142-02 (a second request on a Planning event). If multi-session events are needed, that is a new story for a later sprint. Agreed at standup [date]; Change Log row added. | Arwen
TC-142-12 | Negative | 5 | A missing date blocks submission | Event Approved; assigned coordinator; venue and slot chosen | Unit (venue-booking-service.test.ts), data layer mocked: For the date empty (''), missing (undefined) and blank (' '): 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date, start: '13:00', end: '18:00' }] }) 3. Expect a VALIDATION_ERROR that flags the date; check createVenueBookingRequest was not called Unit (venue-booking-schema.test.ts): the line's error is { date: ['Choose a date.'] } Integration (submit-venue-booking-request.test.ts), real local database: 1. Create an Approved event assigned to the coordinator 2. Call with venueId '' and a line { date: ' ', start: '', end: '' } 3. Expect VALIDATION_ERROR and no rows in Postgres | Date: (empty) / not sent | Not created; 'date' identified as missing (AC5) | Arwen | 27/09/26 | Refused (VALIDATION_ERROR); date flagged; nothing written. | Pass | Automated | Automated: unit (venue-booking-service.test.ts); the all-fields-empty case also run against the real local database. | Arwen
TC-142-12 | Negative | 5 | A missing date blocks submission | Event Approved; assigned coordinator; venue and slot chosen | 1. Leave the date empty 2. Submit | Date: (empty) / not sent | Not created; 'date' identified as missing (AC5) | Arwen | 27/09/26 | Invalid, venue booking request is not valid. Choose a date. | Pass | Manual | Manual: Invalid, venue booking request is not valid. Choose a date. | Arwen
TC-142-13 | Negative | 5 | A missing slot blocks submission | Event Approved; assigned coordinator; venue and date chosen | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '', end: '' }] }) (the start and end times replace the slots) 3. Expect a VALIDATION_ERROR that flags both start and end; check createVenueBookingRequest was not called Integration (submit-venue-booking-request.test.ts), real local database: The all-fields-empty call (see TC-142-12) is also refused with nothing written. | Slots: (none) | Not created; 'slot' identified as missing (AC5) | Arwen | 27/09/26 | Refused (VALIDATION_ERROR): 'Select at least one time slot for this date.'; nothing written. | Pass | Automated | Automated: unit (venue-booking-service.test.ts); the all-fields-empty case also run against the real local database. | Arwen
TC-142-13 | Negative | 5 | A missing slot blocks submission | Event Approved; assigned coordinator; venue and date chosen | 1. Leave all slots unticked 2. Submit | Slots: (none) | Not created; 'slot' identified as missing (AC5) | Arwen | 27/09/26 | Invalid, venue booking request is not valid. Select at least one time slot for this date. | Pass | Manual | Manual: Invalid, venue booking request is not valid. Select at least one time slot for this date. | Arwen
TC-142-14 | Negative | 5 | A missing venue blocks submission | Event Approved; assigned coordinator; date and slot chosen | Unit (venue-booking-service.test.ts), data layer mocked: For the venue empty (''), missing (undefined) and blank (' '): 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-11-15', start: '13:00', end: '18:00' }] }) 3. Expect a VALIDATION_ERROR that flags the venue; check createVenueBookingRequest was not called Integration (submit-venue-booking-request.test.ts), real local database: The all-fields-empty call (see TC-142-12) is also refused with nothing written. | Venue: (empty), not sent, or spaces | Not created; 'venue' identified as missing (AC5) | Arwen | 27/09/26 | Refused (VALIDATION_ERROR): 'Venue must be chosen from the list.'; nothing written. | Pass | Automated | Automated: unit (venue-booking-service.test.ts); the all-fields-empty case also run against the real local database. | Arwen
TC-142-14 | Negative | 5 | A missing venue blocks submission | Event Approved; assigned coordinator; date and slot chosen | 1. Leave the venue empty 2. Submit | Venue: (empty), not sent, or spaces | Not created; 'venue' identified as missing (AC5) | Arwen | 27/09/26 | Refused (VALIDATION_ERROR). Venue must be chosen from the list. | Pass | Manual | Manual (API): Refused (VALIDATION_ERROR). Venue must be chosen from the list. | Arwen
TC-142-15 | Negative | 5 | All missing mandatory fields are reported together | Event Approved; assigned coordinator | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId: '', lines: [{ date: '', start: '', end: '' }] }) 3. Expect a VALIDATION_ERROR whose details name the venue, the date and the start time together; check createVenueBookingRequest was not called Integration (submit-venue-booking-request.test.ts), real local database: 1. Create an Approved event assigned to the coordinator 2. Make the same call 3. Expect VALIDATION_ERROR and no rows in Postgres | Venue, date and slot all empty | Not created; every missing field listed together, not just the first (AC5) | Arwen | 27/09/26 | Venue, date and slot all flagged in one refusal; nothing written. | Pass | Automated | Automated: unit (venue-booking-service.test.ts); the all-fields-empty case also run against the real local database. | Arwen
TC-142-15 | Negative | 5 | All missing mandatory fields are reported together | Event Approved; assigned coordinator | 1. Leave venue, date and slot all empty 2. Submit | Venue, date and slot all empty | Not created; every missing field listed together, not just the first (AC5) | Arwen | 27/09/26 | Refused (VALIDATION_ERROR). Venue must be chosen from the list. Choose a date. Select at least one time slot for this date. | Pass | Manual | Manual (API): Refused (VALIDATION_ERROR). Venue must be chosen from the list. Choose a date. Select at least one time slot for this date. | Arwen
TC-142-16 | Boundary | 5 | A date of only blank spaces is treated as empty | Event Approved; assigned coordinator; venue and slot chosen | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: ' ', start: '13:00', end: '18:00' }] }) 3. Expect a VALIDATION_ERROR that flags the date; check createVenueBookingRequest was not called Unit (venue-booking-schema.test.ts): the line's error is { date: ['Choose a date.'] } Integration (submit-venue-booking-request.test.ts), real local database: The call with date ' ' (see TC-142-12) is refused with nothing written. | Date: ' ' | Not created; 'date' identified as missing (AC5) | Arwen | 27/09/26 | Refused (VALIDATION_ERROR); date flagged; nothing written. | Pass | Automated | Automated: unit (venue-booking-service.test.ts); the all-fields-empty case also run against the real local database. | Arwen
TC-142-16 | Boundary | 5 | A date of only blank spaces is treated as empty | Event Approved; assigned coordinator; venue and slot chosen | 1. Enter spaces into the date 2. Submit | Date: ' ' | Not created; 'date' identified as missing (AC5) | Arwen | 27/09/26 | Refused (VALIDATION_ERROR). The venue booking request is not created. Choose a date. | Pass | Manual | Manual (API): Refused (VALIDATION_ERROR). The venue booking request is not created. Choose a date. | Arwen
TC-142-17 | Boundary | 2, 5 | The approval check takes priority over the missing-field check | Event is Submitted; assigned coordinator | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Draft, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId: '', lines: [{ date: '', start: '', end: '' }] }) 3. Expect the message to say the event must be approved before venue arrangements, with no field details; check createVenueBookingRequest was not called Integration (submit-venue-booking-request.test.ts), real local database: The all-fields-empty call (see TC-142-12) is run on an Approved event, so it checks the field errors; the status-first order is covered by the unit test. | Event status: draft; venue, date and slot all empty | Refused with only the 'must be approved' message; missing-field errors not also shown (AC2 + AC5) | Arwen | 27/09/26 | Now refused with 'must be approved' only, no field details. (First run failed before the fix: the service validated fields before checking status.) | Pass | Automated | Bug found and fixed on this branch (no ticket needed per CLAUDE.md). Automated: unit (venue-booking-service.test.ts); the all-fields-empty case also run against the real local database. | Arwen
TC-142-17 | Boundary | 2, 5 | The approval check takes priority over the missing-field check | Event is Submitted; assigned coordinator | 1. Leave all fields empty 2. Submit | Event status: draft; venue, date and slot all empty | Refused with only the 'must be approved' message; missing-field errors not also shown (AC2 + AC5) | Arwen | 27/09/26 | 400. 'The event must be approved before venue arrangements can begin.' | Pass | Manual | Manual (API): 400. 'The event must be approved before venue arrangements can begin. | Arwen
TC-142-18 | Happy Path | 1 | A valid four-digit-year date is accepted and stored exactly as entered (regression check for SCRUM-258) | Event status is Approved; actor is the assigned coordinator; venue is not retired | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '2026-12-31', start: '09:00', end: '12:00' }] }) 3. Check createVenueBookingRequest received the line unchanged (2026-12-31, 09:00-12:00) and the outcome shows that date with status pending Integration (submit-venue-booking-request.test.ts), real local database: 1. Create an Approved event assigned to the coordinator 2. Make the same call 3. Read back from Postgres: one request with one line 2026-12-31, 09:00:00-12:00:00, status pending | Venue: Bugis Seminar Room; Date: 31 Dec 2026 (2026-12-31); Start: 09:00; End: 12:00 | One request is created for that venue with one line: 2026-12-31, 09:00-12:00, line status Pending; the stored date is the one entered (not moved a day by a time-zone conversion); "Venue booking request submitted" is shown (AC1) | Arwen | 22/10/26 | Unit: the line is written to createVenueBookingRequest as 2026-12-31, 09:00-12:00 and read back as that date, status pending. Integration (real local database): one request row with one line 2026-12-31, 09:00:00-12:00:00, status pending, read back from Postgres. Date not moved a day. | Pass | Automated | Automated: unit (venue-booking-service.test.ts, venue-booking-schema.test.ts) + real local database (submit-venue-booking-request.test.ts). Raised from SCRUM-258 (found on main 4b921f8). Guards the fix: the line date is now a YYYY-MM-DD string checked with isISODate, no longer a Date, so a valid date must still be stored unchanged. 31 Dec is used because a one-day shift would also change the month and year. | Arwen | 22/10/26
TC-142-18 | Happy Path | 1 | A valid four-digit-year date is accepted and stored exactly as entered (regression check for SCRUM-258) | Event status is Approved; actor is the assigned coordinator; venue is not retired | 1. Sign in as the assigned coordinator and open the Approved event's page 2. In "Request a venue", choose a venue 3. In Date, enter 31/12/2026; choose Start 09:00 and End 12:00 4. Click Request venue | Venue: Bugis Seminar Room; Date: 31 Dec 2026 (2026-12-31); Start: 09:00; End: 12:00 | One request is created for that venue with one line: 2026-12-31, 09:00-12:00, line status Pending; the stored date is the one entered (not moved a day by a time-zone conversion); "Venue booking request submitted" is shown (AC1) | Arwen | 22/10/26 | One request is created for that venue with one line: 2026-12-31, 09:00-12:00, line status Pending; the stored date is the one entered (not moved a day by a time-zone conversion); "Venue booking request submitted" is shown. | Pass | Manual | Manual: One request is created for that venue with one line: 2026-12-31, 09:00-12:00, line status Pending; the stored date is the one entered (not moved a day by a time-zone conversion); "Venue booking request submitted" is shown. | Arwen | 22/10/26
TC-142-19 | Negative | 5 | A five-digit year in the line's Date is refused beside the Date field, not with a 500 (SCRUM-258) | Event status is Approved; actor is the assigned coordinator; venue and times chosen | Unit (venue-booking-service.test.ts), data layer mocked: 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '20266-12-10', start: '09:00', end: '12:00' }] }) 3. Expect a VALIDATION_ERROR with lineErrors [{ date: ['Choose a valid date.'] }]; check createVenueBookingRequest was not called Unit (venue-booking-schema.test.ts): the same date gives { date: ['Choose a valid date.'] }; so do 2026-02-30 and 15/11/2026 Integration (submit-venue-booking-request.test.ts), real local database: 1. Create an Approved event assigned to the coordinator 2. Make the same call 3. Expect the same VALIDATION_ERROR; read back from Postgres: no request, and the event is still Approved | Venue: Marina Bay Ballroom; Date: 20266-12-10 (typed 10/12/20266 once max is removed in DevTools); Start: 09:00; End: 12:00 | Step 3: the Date input does not accept a fifth digit in the year. Step 4: refused with a validation error (400 VALIDATION_ERROR), not 500; "Choose a valid date." shown beside that line's Date field in the form; "Something went wrong" is not shown; no request or line row written; the event stays Approved (AC5) | Arwen | 22/10/26 | Unit (service and schema): 20266-12-10 refused, VALIDATION_ERROR, lineErrors [{ date: ['Choose a valid date.'] }], nothing created. Integration (real local database): same refusal; no request row written; event still Approved. Ran against the old code first: both unit cases failed there, as expected. | Pass | Automated | Automated: unit (venue-booking-service.test.ts, venue-booking-schema.test.ts) + real local database (submit-venue-booking-request.test.ts). Also refused: 2026-02-30 and 15/11/2026. TC-142-12 and TC-142-16 still say "Choose a date." for an empty or blank date. Fixed on branch scrum-258-bug. | Arwen | 22/10/26
TC-142-19 | Negative | 5 | A five-digit year in the line's Date is refused beside the Date field, not with a 500 (SCRUM-258) | Event status is Approved; actor is the assigned coordinator; venue and times chosen | 1. Sign in as coordinator@example.com and open an Approved event assigned to you 2. In "Request a venue", choose Marina Bay Ballroom 3. In Date, try to type the year 20266 (10/12/20266). The date input has max="9999-12-31", so the browser stops the year at four digits; note that a five-digit year cannot be typed 4. Open DevTools (F12) > Console, try to insert with invalid date for venue booking request on an Approved event: POST /api/event-requests/<event id>/venue-booking-requests with {"venueId": "<Marina Bay Ballroom id>", "lines": [{"date": "20266-12-10", "start": "09:00", "end": "12:00"}]} | Venue: Marina Bay Ballroom; Date: 20266-12-10 (typed 10/12/20266 once max is removed in DevTools); Start: 09:00; End: 12:00 | Step 3: the Date input does not accept a fifth digit in the year. Step 4: refused with a validation error (400 VALIDATION_ERROR), not 500; "Choose a valid date." shown beside that line's Date field in the form; "Something went wrong" is not shown; no request or line row written; the event stays Approved (AC5) | Arwen | 22/10/26 | Step 3: the Date input does not accept a fifth digit in the year. Step 4: refused with a validation error (400 VALIDATION_ERROR), not 500; "Choose a valid date." shown beside that line's Date field in the form; "Something went wrong" is not shown; no request or line row written; the event stays Approved | Pass | Manual | Manual: Step 3: the Date input does not accept a fifth digit in the year. Step 4: refused with a validation error (400 VALIDATION_ERROR), not 500; "Choose a valid date." shown beside that line's Date field in the form; "Something went wrong" is not shown; no request or line row written; the event stays Approved | Arwen | 22/10/26
TC-142-20 | Boundary | 1, 5 | The last four-digit date (31 Dec 9999) is accepted and the first five-digit date (1 Jan 10000) is refused (SCRUM-258) | Event status is Approved; actor is the assigned coordinator; venue and times chosen | Unit (venue-booking-service.test.ts), data layer mocked: Run A: 1. Mock the event as Approved, assigned to the coordinator 2. Call submitVenueBookingRequest(eventId, coordinatorId, { venueId, lines: [{ date: '9999-12-31', start: '09:00', end: '12:00' }] }) 3. Check the outcome's line date is 9999-12-31 Run B: 1. Make the same call with date '10000-01-01' 2. Expect a VALIDATION_ERROR with lineErrors [{ date: ['Choose a valid date.'] }]; check createVenueBookingRequest was not called Unit (venue-booking-schema.test.ts): 9999-12-31 is accepted and 10000-01-01 is refused Integration (submit-venue-booking-request.test.ts), real local database: Run A: 1. Create an Approved event assigned to the coordinator 2. Call with date '9999-12-31' 3. Read back from Postgres: one request with one pending line 9999-12-31, 09:00:00-12:00:00 Run B: 1. Create another Approved event 2. Call with date '10000-01-01'; expect the same VALIDATION_ERROR 3. Read back from Postgres: no request, and the event is still Approved | Venue: Marina Bay Ballroom; Run A date: 9999-12-31 (typed 31/12/9999); Run B date: 10000-01-01 (typed 01/01/10000 once max is removed in DevTools); Start: 09:00; End: 12:00 | Run A: accepted; one request with one line dated 9999-12-31, status Pending, no error. Run B: the input does not accept a fifth digit (step 5); step 6 is refused with "Choose a valid date." beside the Date field (400 VALIDATION_ERROR, not 500); nothing written; the event stays Approved (AC1, AC5) | Arwen | 22/10/26 | Unit: 9999-12-31 accepted and 10000-01-01 refused (VALIDATION_ERROR, 'Choose a valid date.', nothing created). Integration (real local database): 9999-12-31 stored as one pending line 09:00:00-12:00:00; 10000-01-01 refused, no request row written, event still Approved. | Pass | Automated | Automated: unit (venue-booking-service.test.ts, venue-booking-schema.test.ts) + real local database (submit-venue-booking-request.test.ts). The date input now has max="9999-12-31" (commit d5df532). | Arwen | 22/10/26
TC-142-20 | Boundary | 1, 5 | The last four-digit date (31 Dec 9999) is accepted and the first five-digit date (1 Jan 10000) is refused (SCRUM-258) | Event status is Approved; actor is the assigned coordinator; venue and times chosen | Run A (latest valid date): 1. Sign in as coordinator@example.com and open an Approved event assigned to you 2. In "Request a venue", choose Marina Bay Ballroom 3. In Date, type 31/12/9999 (the year 9999 is accepted by the input); choose Start 09:00 and End 12:00 4. Click Request venue Run B (first date after it), on a different Approved event: 5. Choose Marina Bay Ballroom and try to type 01/01/10000 in Date. The input has max="9999-12-31", so a fifth digit in the year cannot be typed; note this 6. In DevTools (F12) > Console, send a venue booking request with the invalid date 10000-01-01 on an Approved event: POST /api/event-requests/<event id>/venue-booking-requests with {"venueId": "<Marina Bay Ballroom id>", "lines": [{"date": "10000-01-01", "start": "09:00", "end": "12:00"}]} | Venue: Marina Bay Ballroom; Run A date: 9999-12-31 (typed 31/12/9999); Run B date: 10000-01-01 (typed 01/01/10000 once max is removed in DevTools); Start: 09:00; End: 12:00 | Run A: accepted; one request with one line dated 9999-12-31, status Pending, no error. Run B: the input does not accept a fifth digit (step 5); step 6 is refused with "Choose a valid date." beside the Date field (400 VALIDATION_ERROR, not 500); nothing written; the event stays Approved (AC1, AC5) | Arwen | 22/10/26 | Run A: accepted; one request with one line dated 9999-12-31, status Pending, no error. Run B: the input does not accept a fifth digit (step 5); step 6 is refused with "Choose a valid date." beside the Date field (400 VALIDATION_ERROR, not 500); nothing written; the event stays Approved. | Pass | Manual | Manual: Run A: accepted; one request with one line dated 9999-12-31, status Pending, no error. Run B: the input does not accept a fifth digit (step 5); step 6 is refused with "Choose a valid date." beside the Date field (400 VALIDATION_ERROR, not 500); nothing written; the event stays Approved. It stops a fifth digit being typed, but the form has no browser validation, so the server check is reached by sending the request from the Console (step 6). | Arwen | 22/10/26
Rows shaded yellow (TC-142-18 to TC-142-20) were added on 22/10/26 for SCRUM-258. Each test case has an Automated row (steps are the test's own calls) and a Manual row (steps are what a person does in the browser or API).